## Sheet1
		1.8 (win32)	2.0 (win32)	2.0 (x64)
Upgrades	Upgrades successfully from 1.0.3 in QGIS 1.8	PASS	N/A	N/A

Installation	Installs successfully from scratch (direct)	PASS		PASS
	Installs successfully from scratch (with proxy)
	Installation prompts the user to download the viewer manually if installation fails

Layer management	Add layer button should prompt user for layer then load it and zoom to its extent (scalar)			PASS
	Add layer button should prompt user for layer then load it and zoom to its extent (vector)			PASS
	Clicking cancel on the add dialog should bring the user back to the main canvas			PASS
	User can rename the layer			PASS
	User can remove the layer			PASS
	New .dat files added are appended to the appropriate mesh if already loaded			PASS

Project file	Crayfish layer (mesh and multiple .dats) can be saved in project file			PASS
	Crayfish layers saved in project file are restored without error			PASS

Large dataset support	Crayfish recovers gracefully when sufficient memory cannot be allocated for layer			N/A
	No memory leaks appear visible in this situation			N/A

Visualisation	User can change the quantity			PASS
	User can animate through the time steps			PASS
	Displays contour of results			PASS
	Displays vectors of results			PASS
	User can toggle display of both contour and vectors			PASS
	Vector settings function as expected			PASS
	Contour settings function as expected			FAIL	User-defined min and max are not remembered
	Zoom to layer extent works as expected			PASS
	Crayfish value tool displays bed elevation			PASS
	Crayfish value tool displays bed elevation and quantity value inside result zone			PASS
	Crayfish value tool displays nothing outside the mesh extent			PASS
	Transparency slider works as expected			PASS
	Mesh can be toggled			PASS

Projection	Layer takes projection from .prj file in same folder			PASS
	Layer respects users CRS options when prj file is missing			PASS
	User can change the projection of the layer through layer properties			PASS
	Projection-on-the-fly functions as expected			PASS

UI	Dock position is remembered			PASS
	Properties dialog opens as expected			PASS

3rd Party tools	Profile tool works as expected			PASS